## Slide 1: training & Exercises
Testing the plan
Notes: This process is scalable

## Slide 2: Identify the planning team

## Slide 3: Pick a Date
Put the exercise on the calendar
Communicate the date with staff (for announced drills/exercises)
Work backwards
Use a Multi-year calendar
  Develop trends
Don’t cancel it unless there is a major safety reason/Conflict
Notes: There isn’t a right or wrong way to organize for a drill or exercise. What I am going to share with you today, is how I do it. There are things that I do that my go against what exercise planner purists may believe, but I work in healthcare, and I am all about quality products delivered efficiently.
First time drill – communicate date and time

## Slide 4: Identify the purpose?
Identify the purpose of the training/exercise
Determine scope of training/exercise
Write Objectives – s.m.a.r.t.
  Specific
  Measurable
  Achievable
  Realistic
  Time framed

## Slide 5: Type of exercise
Drill
Tabletop exercise
Functional exercise
Full scale exercise

## Slide 6: timeline
What are you expecting to happen from the start of the exercise until the end?
Identify the timeline of events/activities

## Slide 7: Staff preparation
Training
Review policies/procedures
Mini drills
Q & A opportunities

## Slide 8: Make a checklist
Checklist may include:
  Review staffing needs
  Identify what action steps need to be simulated
  Communication with staff
  Identify and schedule training
  Identify and communicate with evaluators
  Schedule a briefing/debriefing
  Reserve a meeting room
  Notify external agencies

## Slide 9: Evaluator preparation
Develop the evaluation
  Should match the procedure/plan that is being tested
Identify areas for observations
Communicate expectations with evaluators
Provide training as needed
Notes: How will you communicate with the evaluators – cell phone, text, walkie talkies, etc.

## Slide 10: Facilitating the exercise
Hold a briefing
  Communicate any last minute changes
determine to what extent you will provide coaching
Stop exercise for life safety reasons
Check in with evaluators

## Slide 11: questions