## Sheet1
Your Healthcare Facility
2014
Oct | Train with COOP Project Team members (individual facilities determine members)
Regional Management Team (RMT) endorsement
Nov | Kick-off meeting with Pilot Site Agenda: Overview, Work Plan, Governance, Identify Critical Departments, Prioritize Departments, Schedules, Questions
Nov - Dec | Pilot Site Survey (Essential services)
2015
Jan | Review results with regional EMC, COOP workgroup, governance, etc.
Jan - Feb | Regional touch point meeting Review pilot sites and determine next steps
Jan - Dec | Begin additional healthcare facility kick-off meetings and essential services surveys. Prioritize and select 2-3 departments.
Jul - Dec | Plan Development
Report out to EMC/RMT, COOP workgroup, governance, etc.
2016-2017
Jan - Dec | Departmental BCP template, Integration and Recovery Strategies, Testing & Exercising, Monitoring & Evaluation
- 96 hour plan - Business Impact Analysis (BIA) - Hazmat Vulnerability Analysis (HVA)
Recommendations to leaders
Additional department surveys (Only 2-3 done in 1st round)
Planning and Management (ongoing)